## Contributor Tracker
Name / Entity | Category | Affiliation | Int/Ext | Contact Window | Channel | First Ask | Quid-pro-quo | Satisfies (requirement) | Constraint / Note | Status
IP waiver inquiry | Gate | UArizona Tech Transfer | Int | 1 · Now–Jun | Direct (tech transfer) | Written acknowledgment Quad/EduCloud is outside appointment scope | Unblocks grants, fiscal sponsor, all binding asks | Gates every binding commitment below | TOP PRIORITY — do first | Not started
Fiscal-sponsor application | Milestone | OSC / SFC | Ext | 3 · Jul–Aug | Application | File once contributor base is live + waiver in hand | Holds IP; nonprofit path; deductible donations | Fiscal sponsorship | Needs Phase-2 contributors active + waiver | Not started
Anchor decision (UArizona vs Willamette) | Decision | — | — | 4 · Sep–Dec | Internal | Resolve home institution | — | Determines CC partner + co-PIs per grant | Settle by late fall, before Jan team-lock | Not started
IUSE ESL Level 1 submission | Milestone | NSF | — | 5 · Dec–Jan | Submission | — | — | — | ~Jan 20, 2027 | Not started
PESOSE Track 1 submission | Milestone | NSF | — | 6 · Jan–Mar | Submission | — | — | — | ~Mar 2, 2027; mandatory I-Corps | Not started
Tyson Swetnam | Strategic partner | UNM (ex-UArizona/CyVerse), MESA PI | Ext | 1 · Now–Jun | Direct (warm) | Confirm MESA integration + UNM partnership posture | MESA EOT layer; facilities framing; mutual | MESA integration; facilities framing | Already broadly on board | Not started
Chemeketa CC transfer partner (name TBD) | CC partner | Chemeketa CC | Ext | 1 · Now–Jun | Via Willamette connections | Open transfer-partnership conversation | Grant subaward; transfer-pathway co-design | IUSE partner (Willamette anchor) + PESOSE user-LOC | Longest lead — name the individual | Not started
Pima CIS 129/185 instructor (name TBD) | CC partner | Pima CC | Ext | 1 · Now–Jun | Via Halvorson-Otts | Open partnership (UArizona-version hedge) | Subaward; pilot site | IUSE partner (UArizona anchor) | Hedge until anchor decision — name individual | Not started
Halvorson-Otts | Connector | Pima CC | Ext | 1 · Now–Jun | Direct | Intro to the Pima CIS instructor | n/a (gatekeeper) | Route to UArizona-version IUSE partner | Confirm | Not started
Ben Markwart | Co-applicant (code) | TBD | Ext | 1 · Now–Jun (build); formalize post-waiver | Direct | Keep building Registry/federation; formalize co-applicant + IP after waiver | Co-applicant credit; co-authorship; governance role | PESOSE / NLnet co-applicant | IP clearance (personal-time/DCO); follows waiver | Not started
Steven Bethard | Code contributor | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Own open-ended grading eval harness + adversarial-submission hardening | Co-authorship (JOSS+venue); deployed tool; capstone/RA | Fiscal-sponsor contributor base + PESOSE contributor-LOC |  | Not started
Peter Jansen | Code contributor | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Own Sol agent-loop interface (Planner→Reasoner→Self-Eval) | Deployed agent-eval env; co-authorship; dataset; allocation | Fiscal-sponsor contributor base + PESOSE contributor-LOC |  | Not started
Adarsh Pyarelal | Code contributor | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Own model-layer interface + trace-as-research artifact | Human-AI dataset; co-authorship; reproducibility; NAIRR/ACCESS | Fiscal-sponsor contributor base + PESOSE contributor-LOC |  | Not started
Clayton Morrison | Code contributor | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Own grading calibration / abstain gate | Methods paper; standing benchmark; RA | Fiscal-sponsor contributor base + PESOSE contributor-LOC |  | Not started
Egoitz Laparra | Code contributor | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | NLP plumbing / grounding (RAG-on-OER) + trace tooling | Budgeted senior-personnel role + co-authorship | Contributor base + possible budgeted IUSE/PESOSE personnel | Quid is budgeted effort, not glory | Not started
Xiao Hu | Direction | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Co-design learner model + analytics; own equity audit | LAK/EDM dataset; analytics+equity papers; senior personnel | IUSE senior personnel (learning-analytics eval) |  | Not started
John Chen | Direction | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Co-own Sol interaction design + stance-as-config study | Co-authorship; deployment+traces; capstone/RA | Direction + possible senior personnel |  | Not started
Winslow Burleson | Direction | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Senior steer on Sol + human-peer-feedback channel | Named senior/advisory role; co-authorship | Direction + IUSE senior personnel (gravitas) |  | Not started
Barney Maccabe | Direction / sponsor | UArizona InfoSci (Assoc Dean Research) | Int | 2 · Late Jun–Jul | Direct | Advisory on CI / sandbox / scale + data policy | College-attributable CI win; allocation support | Direction/sponsor; possible facilities | Dean-level door | Not started
Lucas Cordova | Sol co-design / co-PI | Willamette | Ext | 2 · Late Jun–Jul | Direct email | Sol co-design (guardrailed tutor) | Co-PI on Sol/AI thread; co-authorship | IUSE co-PI (Sol thread) + faculty-position opening |  | Not started
Forgejo / Codeberg maintainers | OSS community | Forgejo / Codeberg | Ext | 2 · Late Jun–Jul | Drafted proposal (quad-forgejo-proposal.html) | Propose federation co-implementation | Shared standard; NLnet co-applicant | PESOSE contributor-LOC + NLnet path + fiscal-sponsor community | Outreach already drafted | Not started
External devs (1–2, GitLab adapter) | OSS community | Community | Ext | 2 · Late Jun–Jul | Good-first-issues / recruit | Take GitLab-adapter good-first-issues | OSS credit; co-authorship | PESOSE contributor-LOC + fiscal-sponsor community |  | Not started
MESA cohort instructors / Educator Fellows | Adopter | UArizona / MESA | Int | 3 · Jul–Aug | Direct / MESA channel | Lock Fall pilot courses | Free graded assignment layer; support | PESOSE user-LOC; IUSE pilot sites | Captive first users | Not started
Oregon Tech contact | Adopter | Oregon Tech | Ext | 3 · Jul–Aug | Direct | Confirm Fall pilot | Free tool; support; case study | PESOSE user-LOC / IUSE pilot site |  | Not started
Furman contact | Adopter | Furman | Ext | 3 · Jul–Aug | Direct | Confirm Fall pilot | Free tool; support; case study | PESOSE user-LOC / IUSE pilot site |  | Not started
Willamette pilot users | Adopter | Willamette | Ext | 3 · Jul–Aug | Direct | Confirm Fall pilot | Free tool; support; case study | PESOSE user-LOC / IUSE pilot site |  | Not started
Mine Doğucu | Adopter + senior personnel | Harvard | Ext | 3 · Jul–Aug | Via 3C (warm intro) | Adopter + IUSE senior personnel | Senior personnel; co-authorship; dataset | IUSE senior personnel + PESOSE user-LOC | KEEP OFF PESOSE proposing team; confirm role | Not started
Rasika Bhalerao | Adopter + senior personnel | Northeastern | Ext | 3 · Jul–Aug | Via 3C (warm intro) | Adopter + IUSE senior personnel | Senior personnel; security fit; co-authorship | IUSE senior personnel + PESOSE user-LOC | KEEP OFF PESOSE proposing team; confirm role | Not started
Gulustan Dogan | Contributor (letter) | UNCW | Ext | 3 · Jul–Aug (contact); Sep–Dec (contribute) | Direct | Recruit as genuine contributor | Contributor credit; co-authorship | PESOSE contributor-LOC | Must genuinely contribute in Fall | Not started
Carpentries / RSE community | Contributor + dissemination | Community | Ext | 3 · Jul–Aug | Listserv / community announce | Recruit contributors; announce | Tool for community; recognition | PESOSE contributor-LOC + dissemination |  | Not started
Heather Kitada Smalley | Co-PI (lead, Willamette) | Willamette | Ext | 4 · Sep–Dec | Direct | Confirm lead Willamette IUSE co-PI | Co-PI; research leadership | IUSE lead co-PI (Willamette anchor) | Follows waiver + anchor decision | Not started
Fred Agbo | Co-PI (alt) | Willamette | Ext | 4 · Sep–Dec | Direct | Confirm co-PI / intro-Python bridge | Co-PI / senior personnel | IUSE co-PI alternate | Follows waiver + anchor decision | Not started
Haiyan Cheng | Senior personnel | Willamette | Ext | 4 · Sep–Dec | Direct | Ethics / social-good role | Senior personnel; co-authorship | IUSE senior personnel |  | Not started
Skye Morét / PNCA Make+Think+Code | Design partner | PNCA | Ext | 3–4 · Jul–Dec | Direct | Design / viz partnership | Collaboration; co-design | Design direction + SCIS–PNCA bridge |  | Not started
Angela Cruze | Co-PI (PESOSE, governance) | TBD | Ext | 4 · Sep–Dec | Direct | Confirm PESOSE co-PI | Co-PI role | PESOSE co-PI | Resolve affiliation (internal vs subaward) | Not started
Regina Deil-Amen | Senior personnel (transfer/equity) | UArizona (Education) | UA non-InfoSci | 4 · Sep–Dec | Direct | Transfer / equity research collaboration | Co-authorship; study collaboration | IUSE research depth | Confirm role | Not started
CRED team | Evaluator | UArizona | UA non-InfoSci | 4 · Sep–Dec | Direct | External evaluator for the study | Evaluation role / contract | IUSE / PESOSE external evaluator |  | Not started
CyVerse / UArizona infrastructure contact | Facilities | UArizona / CyVerse | UA non-InfoSci | 4 · Sep–Dec | Direct | Facilities-letter commitment | Showcased infrastructure use | PESOSE facilities letter |  | Not started
Request PESOSE letters (≥3, ≤5) | Action | from Fall users/contributors | — | 5 · Dec–Jan | Direct | Hand each their activity notes; request LOC | — | PESOSE hard requirement | Genuine Fall users/contributors only; not the team | Not started
Lock IUSE team + List of Project Participants | Action | — | — | 5 · Dec–Jan | Internal | Finalize lead co-PI + CC partner + senior personnel | — | IUSE submission packet |  | Not started
Gus Hahn-Powell | Code (secondary) | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | NLP tooling for Sol (secondary) | Co-authorship; contributor credit | Optional code pool |  | Hold/optional
Jialu Li | Code (secondary) | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Speech / multilingual Sol dimension (if scoped) | Co-authorship | Optional, scope-dependent |  | Hold/optional
Ann Shivers-McNair | Design direction | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Dashboard UX + governance seam | Co-design; co-authorship | Optional design direction |  | Hold/optional
Cristian Román | Applied / curriculum | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Applied ML code + MSDS curriculum reach | Co-authorship; adoption reach | Optional; adoption lever |  | Hold/optional
Sara Riazi | Applied / data eng | UArizona InfoSci | Int | 2 · Late Jun–Jul | Direct email | Data-engineering code (extra hands) | Co-authorship; contributor credit | Optional code pool |  | Hold/optional

## Legend
Quad / Sol — Contributor Tracker
Two anchoring principles
1. IP waiver gates every binding commitment | co-PI agreements, fiscal-sponsor signing, Markwart's co-applicant IP — but NOT exploratory contributor/adopter outreach
2. Adoption precedes letters | you can't request a credible LOC from someone who hasn't used/built on Quad; Fall-2026 pilots are the engine
Fixed deadlines
IUSE ESL Level 1 | ~Jan 20, 2027 (third Wednesday in January)
PESOSE Track 1 | ~Mar 2, 2027 (≥3 external LOCs; mandatory I-Corps)
GitHub Classroom sunset | Aug 28, 2026 — the adopter recruiting catalyst
Contact-window phases (sort the Contact Window column)
1 · Now–Jun | Gate + longest leads (waiver, Swetnam, CC partners, Markwart)
2 · Late Jun–Jul | Code contributors + Sol direction + OSS + Cordova
3 · Jul–Aug | Adopters, timed to the GHC sunset; fiscal-sponsor filing
4 · Sep–Dec | Fall pilots run — nurture + deepen co-PI/eval/facilities
5 · Dec–Jan | Convert to letters; lock IUSE team; IUSE submission
6 · Jan–Mar | Finalize + submit PESOSE
Status values | Not started · Queued · Contacted · In progress · Confirmed · Declined · Hold/optional · Done
Note | Parchment rows = gates/milestones/decisions/actions (not people). Gray rows = optional InfoSci pool (on hold).